## Product Backlog
Backlog ID | Feature | Work Item | Priority | Story Points | Sprint | Status | Assignee | Description
PB-001 | Project Setup | Create GitHub Repo | High | 5 | Sprint 1 | To Do | Kaushal Dwivedi | Create GitHub Repo for Project Setup
PB-002 | Project Setup | Setup Frontend | High | 5 | Sprint 1 | To Do | Kaushal Dwivedi | Setup Frontend for Project Setup
PB-003 | Project Setup | Setup Backend | High | 5 | Sprint 1 | To Do | Kaushal Dwivedi | Setup Backend for Project Setup
PB-004 | Project Setup | Configure MongoDB | High | 5 | Sprint 1 | To Do | Kaushal Dwivedi | Configure MongoDB for Project Setup
PB-005 | Project Setup | Setup CI/CD | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Setup CI/CD for Project Setup
PB-006 | Project Setup | Create Folder Structure | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Create Folder Structure for Project Setup
PB-007 | Project Setup | Environment Config | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Environment Config for Project Setup
PB-008 | Project Setup | Coding Standards | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Coding Standards for Project Setup
PB-009 | Project Setup | Initial Documentation | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Initial Documentation for Project Setup
PB-010 | Project Setup | Project Kickoff | Medium | 3 | Sprint 1 | To Do | Kaushal Dwivedi | Project Kickoff for Project Setup
PB-011 | User Authentication | User Registration | High | 5 | Sprint 2 | To Do | Kaushal Dwivedi | User Registration for User Authentication
PB-012 | User Authentication | User Login | High | 5 | Sprint 2 | To Do | Kaushal Dwivedi | User Login for User Authentication
PB-013 | User Authentication | Forgot Password | High | 5 | Sprint 2 | To Do | Kaushal Dwivedi | Forgot Password for User Authentication
PB-014 | User Authentication | Reset Password | High | 5 | Sprint 2 | To Do | Kaushal Dwivedi | Reset Password for User Authentication
PB-015 | User Authentication | Logout | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | Logout for User Authentication
PB-016 | User Authentication | Email Verification | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | Email Verification for User Authentication
PB-017 | User Authentication | JWT Auth | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | JWT Auth for User Authentication
PB-018 | User Authentication | Role Management | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | Role Management for User Authentication
PB-019 | User Authentication | Session Mgmt | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | Session Mgmt for User Authentication
PB-020 | User Authentication | Profile Setup | Medium | 3 | Sprint 2 | To Do | Kaushal Dwivedi | Profile Setup for User Authentication
PB-021 | Home Page | Navbar | High | 5 | Sprint 3 | To Do | Kaushal Dwivedi | Navbar for Home Page
PB-022 | Home Page | Hero Banner | High | 5 | Sprint 3 | To Do | Kaushal Dwivedi | Hero Banner for Home Page
PB-023 | Home Page | Featured Products | High | 5 | Sprint 3 | To Do | Kaushal Dwivedi | Featured Products for Home Page
PB-024 | Home Page | Categories | High | 5 | Sprint 3 | To Do | Kaushal Dwivedi | Categories for Home Page
PB-025 | Home Page | Footer | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | Footer for Home Page
PB-026 | Home Page | Responsive UI | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | Responsive UI for Home Page
PB-027 | Home Page | Testimonials | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | Testimonials for Home Page
PB-028 | Home Page | Promo Banner | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | Promo Banner for Home Page
PB-029 | Home Page | Search Bar | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | Search Bar for Home Page
PB-030 | Home Page | CTA Section | Medium | 3 | Sprint 3 | To Do | Kaushal Dwivedi | CTA Section for Home Page
PB-031 | Product Catalog | Product Listing | High | 5 | Sprint 4 | To Do | Kaushal Dwivedi | Product Listing for Product Catalog
PB-032 | Product Catalog | Product Details | High | 5 | Sprint 4 | To Do | Kaushal Dwivedi | Product Details for Product Catalog
PB-033 | Product Catalog | Categories | High | 5 | Sprint 4 | To Do | Kaushal Dwivedi | Categories for Product Catalog
PB-034 | Product Catalog | Inventory Display | High | 5 | Sprint 4 | To Do | Kaushal Dwivedi | Inventory Display for Product Catalog
PB-035 | Product Catalog | Image Gallery | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | Image Gallery for Product Catalog
PB-036 | Product Catalog | Reviews | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | Reviews for Product Catalog
PB-037 | Product Catalog | Related Products | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | Related Products for Product Catalog
PB-038 | Product Catalog | Pagination | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | Pagination for Product Catalog
PB-039 | Product Catalog | API Integration | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | API Integration for Product Catalog
PB-040 | Product Catalog | Error Handling | Medium | 3 | Sprint 4 | To Do | Kaushal Dwivedi | Error Handling for Product Catalog
PB-041 | Search & Filters | Search Products | High | 5 | Sprint 5 | To Do | Kaushal Dwivedi | Search Products for Search & Filters
PB-042 | Search & Filters | Filter Category | High | 5 | Sprint 5 | To Do | Kaushal Dwivedi | Filter Category for Search & Filters
PB-043 | Search & Filters | Filter Price | High | 5 | Sprint 5 | To Do | Kaushal Dwivedi | Filter Price for Search & Filters
PB-044 | Search & Filters | Filter Availability | High | 5 | Sprint 5 | To Do | Kaushal Dwivedi | Filter Availability for Search & Filters
PB-045 | Search & Filters | Sort Products | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Sort Products for Search & Filters
PB-046 | Search & Filters | Auto Suggest | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Auto Suggest for Search & Filters
PB-047 | Search & Filters | Reset Filters | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Reset Filters for Search & Filters
PB-048 | Search & Filters | Search History | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Search History for Search & Filters
PB-049 | Search & Filters | Advanced Filters | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Advanced Filters for Search & Filters
PB-050 | Search & Filters | Performance | Medium | 3 | Sprint 5 | To Do | Kaushal Dwivedi | Performance for Search & Filters
PB-051 | Shopping Cart | Add to Cart | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Add to Cart for Shopping Cart
PB-052 | Shopping Cart | Remove Item | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Remove Item for Shopping Cart
PB-053 | Shopping Cart | Update Qty | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Update Qty for Shopping Cart
PB-054 | Shopping Cart | View Cart | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | View Cart for Shopping Cart
PB-055 | Shopping Cart | Save Cart | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Save Cart for Shopping Cart
PB-056 | Shopping Cart | Cart Validation | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Cart Validation for Shopping Cart
PB-057 | Shopping Cart | Rental Duration | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Rental Duration for Shopping Cart
PB-058 | Shopping Cart | Price Calc | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Price Calc for Shopping Cart
PB-059 | Shopping Cart | Empty Cart | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Empty Cart for Shopping Cart
PB-060 | Shopping Cart | Cart Testing | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Cart Testing for Shopping Cart
PB-061 | Checkout & Payments | Checkout Page | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Checkout Page for Checkout & Payments
PB-062 | Checkout & Payments | Address | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Address for Checkout & Payments
PB-063 | Checkout & Payments | Order Summary | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Order Summary for Checkout & Payments
PB-064 | Checkout & Payments | Payment Gateway | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Payment Gateway for Checkout & Payments
PB-065 | Checkout & Payments | Coupon | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Coupon for Checkout & Payments
PB-066 | Checkout & Payments | Invoice | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Invoice for Checkout & Payments
PB-067 | Checkout & Payments | Payment Success | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Payment Success for Checkout & Payments
PB-068 | Checkout & Payments | Payment Failure | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Payment Failure for Checkout & Payments
PB-069 | Checkout & Payments | Order Confirmation | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Order Confirmation for Checkout & Payments
PB-070 | Checkout & Payments | Email Receipt | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Email Receipt for Checkout & Payments
PB-071 | User Dashboard | View Profile | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | View Profile for User Dashboard
PB-072 | User Dashboard | Edit Profile | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Edit Profile for User Dashboard
PB-073 | User Dashboard | Order History | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Order History for User Dashboard
PB-074 | User Dashboard | Wishlist | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Wishlist for User Dashboard
PB-075 | User Dashboard | Rental Tracking | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Rental Tracking for User Dashboard
PB-076 | User Dashboard | Notifications | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Notifications for User Dashboard
PB-077 | User Dashboard | Settings | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Settings for User Dashboard
PB-078 | User Dashboard | Downloads | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Downloads for User Dashboard
PB-079 | User Dashboard | Support | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Support for User Dashboard
PB-080 | User Dashboard | Delete Account | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Delete Account for User Dashboard
PB-081 | Admin Dashboard | Admin Login | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Admin Login for Admin Dashboard
PB-082 | Admin Dashboard | Manage Products | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Manage Products for Admin Dashboard
PB-083 | Admin Dashboard | Manage Users | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Manage Users for Admin Dashboard
PB-084 | Admin Dashboard | Manage Orders | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Manage Orders for Admin Dashboard
PB-085 | Admin Dashboard | Reports | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Reports for Admin Dashboard
PB-086 | Admin Dashboard | Inventory | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Inventory for Admin Dashboard
PB-087 | Admin Dashboard | Discounts | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Discounts for Admin Dashboard
PB-088 | Admin Dashboard | CMS | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | CMS for Admin Dashboard
PB-089 | Admin Dashboard | Audit Logs | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Audit Logs for Admin Dashboard
PB-090 | Admin Dashboard | Admin Settings | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Admin Settings for Admin Dashboard
PB-091 | Testing & Deployment | Unit Testing | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Unit Testing for Testing & Deployment
PB-092 | Testing & Deployment | Integration Testing | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Integration Testing for Testing & Deployment
PB-093 | Testing & Deployment | Bug Fixing | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | Bug Fixing for Testing & Deployment
PB-094 | Testing & Deployment | UAT | High | 5 | Sprint 6 | To Do | Kaushal Dwivedi | UAT for Testing & Deployment
PB-095 | Testing & Deployment | Frontend Deploy | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Frontend Deploy for Testing & Deployment
PB-096 | Testing & Deployment | Backend Deploy | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Backend Deploy for Testing & Deployment
PB-097 | Testing & Deployment | DB Migration | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | DB Migration for Testing & Deployment
PB-098 | Testing & Deployment | Monitoring | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Monitoring for Testing & Deployment
PB-099 | Testing & Deployment | Documentation | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Documentation for Testing & Deployment
PB-100 | Testing & Deployment | Release | Medium | 3 | Sprint 6 | To Do | Kaushal Dwivedi | Release for Testing & Deployment
PB-101 | Testing & Deployment | Security Review | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Security Review
PB-102 | Testing & Deployment | Performance Optimization | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Performance Optimization
PB-103 | Testing & Deployment | Accessibility | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Accessibility
PB-104 | Testing & Deployment | SEO Basics | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | SEO Basics
PB-105 | Testing & Deployment | Analytics | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Analytics
PB-106 | Testing & Deployment | Backup | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Backup
PB-107 | Testing & Deployment | Logging | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Logging
PB-108 | Testing & Deployment | API Docs | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | API Docs
PB-109 | Testing & Deployment | Release Notes | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Release Notes
PB-110 | Testing & Deployment | Retrospective | Medium | 2 | Sprint 6 | To Do | Kaushal Dwivedi | Retrospective